## Main
Scope of Work Activity Covered by this Work Method Statement | [8 empty] | Site:
This Work Method Statement outlines the main hazards and risks associated with |  |  |  |  | General Works
Instructions for Safe Work Method Statements
A Safe Work Method Statement (SWMS) is a document that sets out the work activities to be carried out at a workplace, the hazards arising from these activities and the measures to be put in place to control the risks. All work must be carried out in accordance with this SWMS. This SWMS must be kept and be available for inspection.
Applicable High Risk Construction Work Activities (highlighted). A SWMS is required for all high risk work activities.
Y | A risk of a person falling more than 2 M |  |  | Y | Demolition of a load-bearing structure. |  |  |  |  | Work on a tele-communications tower
Y | Work in or near a shaft or thrench with an excavated depth over 1.5m or in a tunnel |  |  |  | Temporary load-bearing support structures for structural installations or repairs |  |  |  | Y | Work on or near a pressurised gas distribution mains or piping
| Work on or near chemical, fuel or refrigerant lines |  |  |  | Work on, in or adjacent to a road, railway, shipping lane or other traffic corridor in use by traffic other than pedestrians |  |  |  | Y | Work on or near energised electrical installations or services
| Likely to involve disturbing asbestos |  |  |  | Work in or near a confined space |  |  |  | Y | Work in an area with movement of powered mobile plant
| Work in areas with artificial extremes of temperature |  |  |  | Work in or near water or other liquid that involves a risk of drowning |  |  |  |  | Work in an area that may have a contaminated or flammable atmosphere
| Use of explosives |  |  |  | Tilt-up or precast concrete elements |  |  |  |  | Diving work
Personal Protective Clothing & Equipment (PPE) Required
|  |  | Safety Boots |  |  |  | Protective Gloves
|  |  | Safety Glasses |  |  |  | High Visibility Clothing / Vests
|  |  | Hearing Protection |  |  |  | Hard Hat
Required Qualifications/Verifications
|  |  | Qualification |  |  | Requirement |  | Qualification |  |  |  | Requirement
|  |  | WHSQE Induction |  |  | All Personnel |  | High Risk Licence - Working at Heights |  |  |  | Where Required
|  |  | Construction Industry White Card |  |  | All Personnel |  | High Risk Lisence- Elevated Work Platform |  |  |  | Where Required
|  |  | Site Induction |  |  | All Personnel
Required Qualifications/Verifications
Plant and equipment used on site includes, but is not limited to:
|  |  | Plant and/or Equipment |  | Inspection and maintenance checks required |  |  | Plant and/or Equipment |  |  | Inspection and maintenance checks required
|  |  | Mobile Equipment |  | Safety check prior to use. Maintenance & Safety Checks in accordanxce with Maniufacturers Specifications |  |  | Electrical Equipment |  |  | Tag & Test. Safety check prior to use. Maintenance & Safety Checks in accordanxce with Maniufacturers Specifications
|  |  | Ladders |  | Safety check prior to use |  |  | Extension Leads |  |  | Tag & Test Safety check prior to use
|  |  | Lifting Equipment |  | Safety check prior to use |  |  | Hand Tools |  |  | Safety check prior to use. Maintenance & Safety Checks in accordanxce with Maniufacturers Specifications
Inspections of plant to be carried out before commencement of work, as per listed hazard controls for pre-start checks.
| SWMS Develop By: | Mark Veenendaal |  |  | SWMS Approved By: |  |  | Anthony Agius
| SWMS Consulted With: | Site Foreman |  |  | Person Responsible for ensuring compliance with this SWMS |  |  | Site Foreman
Formal communication of Site Safety Rules will occur primarily in three ways:
1. As part of the implementation of this Work Method Statement, all parties in the workgroup to be present for a brief meeting.
2. As new person(s) (employees, subcontractors, etc.) enter the site for the first time they will be briefed on the Site Safety Rules that they must comply with and sign induction form stating that they are aware of the site specific hazards.
3. At regular ‘toolbox’ meetings – employees will be reminded of the safety site rules, new and existing potential hazards and also constantly reminded of the importance of striving for a hazard free work place.

## NSW
Relevant Legislation, Standards & Codes of Practice relating to the work:
NSW Work Health & Safety Act November 2011
NSW Work Health & Safety Regulations September 2025
|  | NSW Code of Practice - | Construction Work | August, 2019
|  | NSW Code of Practice - | Demolition | August, 2019
|  | NSW Code of Practice - | Elevating Work Platforms | July,2026
|  | NSW Code of Practice - | Excavation Work | January, 2020
|  | NSW Code of Practice - | First Aid in the Workplace | January, 2020
|  | NSW Code of Practice - | Hazardous Manual Tasks | August, 2019
|  | NSW Code of Practice - | How to Manage and Control Asbestos in the Workplace | December, 2022
|  | NSW Code of Practice - | How to Safely Remove Asbestos December | December, 2022
|  | NSW Code of Practice - | How to Manage Work Health and Safety Risks | August, 2019
|  | NSW Code of Practice - | Managing Electrical Risks in the Workplace | August, 2019
|  | NSW Code of Practice - | Managing Noise & Preventing Hearing Loss at Work | December, 2022
|  | NSW Code of Practice - | Managing the Risk of Falls in Housing Construction | August, 2019
|  | NSW Code of Practice - | Managing the Risks of Hazardous Chemicals in the Workplace | December, 2022
|  | NSW Code of Practice - | Managing the Risks of Plant in the Workplace | December, 2022
|  | NSW Code of Practice - | Managing the Work Environment and Facilities | August, 2019
|  | NSW Code of Practice - | Moving Plant on Construction Sites | December, 2025
|  | NSW Code of Practice - | Work Health and Safety Consultation, Cooperation and Coordination | December, 2022
|  | NSW Code of Practice - | Working Safely when Cutting, Drilling and Grinding Concrete and Masonry Products | May, 2026
|  | NSW Code of Practice - | Work Near Overhead and Underground Electric Lines | May, 2026
|  | NSW Code of Practice - | Work on Roofs — Commercial and Industrial Buildings | May, 2026
| Traffic Control at Work Sites TS 05492:1.0 |  |  | June, 2026

## NT (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
NT Work Health & Safety (National Uniform Legislation) Act 2011
NT Work Health & Safety (National Uniform Legislation) Regulations 2011
NT Code of Practice - Confined Space September 2019
NT Code of Practice - First Aid in the Workplace September 2019
NT Code of Practice - Hazardous Manual Tasks September 2019
NT Code of Practice - How to Manage Work Health and Safety Risks September 2019
NT Code of Practice - Managing Noise & Preventing Hearing Loss at Work September 2019
NT Code of Practice - Managing the Risk of Falls at Workplaces September 2019
NT Code of Practice - Managing the Risks of Hazardous Chemicals in the Workplace September 2019
NT Code of Practice - Managing the Risks of Plant in the Workplace September 2019
NT Code of Practice - Managing the Work Environment and Facilities September 2019
NT Code of Practice - Work Health and Safety Consultation, Cooperation and Coordination November 2019

## QLD (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
QLD Work Health & Safety Act November 2011
QLD Work Health and Safety and Other Legislation Amendment Act 2015
QLD Work Health and Safety and Other Legislation Amendment Act 2017
QLD Work Health & Safety Regulations November 2017
QLD Work Health & Safety Regulations Amendments 2016
QLD Work Health & Safety Regulations Exemptions
QLD Work Health & Safety Regulations Transitional Provisions
QLD Code of Practice - Demolition July 2018
QLD Code of Practice - Excavation March 2021
QLD Code of Practice - First Aid in the Workplace March 2021
QLD Code of Practice - Hazardous Manual Tasks March 2021
QLD Code of Practice - How to Manage Work Health and Safety Risks March 2021
QLD Code of Practice - Managing Electrical Risks in the Workplace March 2021
QLD Code of Practice - Managing Noise & Preventing Hearing Loss at Work July 2018
QLD Code of Practice - Managing the Risk of Falls at Workplaces March 2021
QLD Code of Practice - Managing the Risks of Hazardous Chemicals in the Workplace January 2023
QLD Code of Practice - Managing the Risks of Plant in the Workplace March 2021
QLD Code of Practice - Managing the Work Environment and Facilities March 2021
QLD Code of Practice - Traffic Management for Construction or Maintenance Work July 2018
QLD Code of Practice - Work Health and Safety Consultation, Cooperation and Coordination August 2022

## SA (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
SA Work Health & Safety Act November 2012
SA Work Health & Safety Regulations November 2012
SA Code of Practice - Confined Space February 2014
SA Code of Practice - Demolition March 2015
SA Code of Practice - First Aid in the Workplace March 2019
SA Code of Practice - Hazardous Manual Tasks December 2011
SA Code of Practice - How to Manage Work Health and Safety Risks March 2019
SA Code of Practice - Managing Electrical Risks in the Workplace March 2015
SA Code of Practice - Managing Noise & Preventing Hearing Loss at Work December 2011
SA Code of Practice - Managing the Risk of Falls at Workplaces March 2015
SA Code of Practice - Managing the Risks of Hazardous Chemicals in the Workplace March 2019
SA Code of Practice - Managing the Risks of Plant in the Workplace March 2019
SA Code of Practice - Managing the Work Environment and Facilities March 2019
SA Code of Practice - Welding Processes March 2019
SA Code of Practice - Work Health and Safety Consultation, Cooperation and Coordination March 2019

## TAS (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
TAS Work Health & Safety Act April 2012
TAS Work Health & Safety (Transitional and Consequential Provisions) Act April 2012
TAS Work Health & Safety Regulations December 2012
TAS Work Health & Safety (Transitional) Regulations December 2012
TAS Code of Practice - Confined Space December 2018
TAS Code of Practice - Demolition December 2018
TAS Code of Practice - First Aid in the Workplace December 2018
TAS Code of Practice - Hazardous Manual Tasks December 2018
TAS Code of Practice - How to Manage Work Health and Safety Risks December 2018
TAS Code of Practice - Managing Electrical Risks in the Workplace December 2018
TAS Code of Practice - Managing Noise & Preventing Hearing Loss at Work December 2018
TAS Code of Practice - Managing the Risk of Falls at Workplaces December 2018
TAS Code of Practice - Managing the Risks of Hazardous Chemicals in the Workplace December 2018
TAS Code of Practice - Managing the Risks of Plant in the Workplace December 2018
TAS Code of Practice - Managing the Work Environment and Facilities December 2018
TAS Code of Practice - Welding Processes December 2018
TAS Code of Practice - Work Health and Safety Consultation, Cooperation and Coordination December 2018

## VIC (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
VIC Occupational Health & Safety Act December 2004
Vic Occupational Health and Safety and Other Legislation Amendment Act 2021
VIC Occupational Health & Safety Regulations October 2017
Vic Compliance Code - Demolition December 2019
Vic Compliance Code - Excavation December 2019
Vic Compliance Code - First Aid in the Workplace November 2021
Vic Compliance Code - Hazardous Manual Handling December 2019
Vic Compliance Code - Hazardous Substances December 2019
Vic Compliance Code - Noise December 2019
Vic Compliance Code - Plant December 2019
Vic Compliance Code - Prevention of Falls in General Construction December 2019
Vic Compliance Code - Workplace Amenities and Work Environment September 2008

## WA (hidden)
Relevant Legislation, Standards & Codes of Practice relating to the work:
WA Occupational Health & Safety Act December 1984
WA Occupational Health & Safety Regulations September 1996
WA Code of Practice - Control of Workplace Hazardous Substances 2007
WA Code of Practice - First Aid Facilities and Services; Workplace Amenities and Facilities; Personal Protective Clothing 2002
WA Code of Practice - Health & Safety in Welding 2013
WA Code of Practice - Managing Electrical Risks in the Workplace August 2019
WA Code of Practice - Manual Tasks August 2010
WA Code of Practice - Prevention of Falls at Workplaces 2004

## Site Establishment
Site Establishment
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Site Establishment | All workers unaware of site issues. Slips trips and falls Manual Handling Noise Fatigue | 3 | 4 | H7 | 1 - Work activity will be booked for the day with site management. 2 - All workers to sign in if required be management. Site office or muster point to be established with all required information including induction and sign in to be available to all staff attending site. 3 - Toolbox talks 4 - Ensure site rules are adhered to at all times. 5 - Ensure site traffic management is adhered to 6 - Correct PPE to be worn - Site Safety Rules 7 - Site Working Hours | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Site Establishment | Excavation & Burried Services | 3 | 4 | H7 | 1 - Ensure HAZMAT register has been reviewed and all workers are aware if any ACM or HAZMAT material are present. 2 - If applicable HAZMAT Management plan to be incorporated or devised. 3 - If HAZMAT has been identified during the works, material is to be tested to be identified if it is positive and then a Management plan is to be incorporated in the removal/remediation or management of the identified material. | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Site Establishment | Hot Work - Fire, Explosion | 3 | 5 | H8 | Hot work permit system including observer | Site Supervision All Workers | 1 | 5 | M6 |  | 0 | 1 | 0 | 0
Site Establishment | HAZMAT (contamination from ACM, Lead). | 3 | 4 | H7 | 1 - Ensure HAZMAT register has been reviewed and all workers are aware if any ACM or HAZMAT material are present. 2 - If applicable HAZMAT Management plan to be incorporated or devised. 3 - If HAZMAT has been identified during the works, material is to be tested to be identified if it is positive and then a Management plan is to be incorporated in the removal/remediation or management of the identified material 4 - Lead dust over 1% concentration requires a lead work permit. | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Access & Egress - Traffic Management | Injury due to Vehicle Collision - Collision with pedestrians and site vehicles | 3 | 4 | H7 | 1 - Traffic Management Plan 2 - Area to be barricaded/fenced from unauthorised access. | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Emergency | Fire, - Flood, Explosion (gas, equipment, hazardous goods, bomb), Spills (oils, chemicals etc), Building Collapse, Civil Unrest, Natural disaster | 3 | 5 | H8 | 1 - Work Health & Safety Management Plan 2 - Site Evactuation Plan 3 - Traffic Management Plan 4 - Site Induction | Site Supervision All Workers | 1 | 5 | M6 | Y | 0 | 1 | 0 | 0
Unloading Equipment | Fall from vehicle Manual Handling injury Sprains Strains and Falls | 3 | 3 | M6 | 1 - Manual handling The use of PPE equipment such as gloves are needed. Team lifting where required and manual handling aids when possible. 2 - Use of correct lifting technique when carrying out work. 3 - Ensure stretching and warm up prior to work being carried out. 4 - Reference SafeWork NSW COP Hazardous Manual Handling | Site Supervision All Workers | 1 | 3 | L4 | Y | 1 | 0 | 0 | 0
Overhead Wires | Electrocution | 3 | 5 | H8 | 1 - Overhead Wires Identified Using "Tiger Tails" 2 - Safe Distance Assessment - Mandatory Minimum Approach Distances As Per SafeWork NSW COP Working Near Overhead Power Lines 3 - Use of Observer 4 - Safe Effective Hazardous Working at Heights Procedures 5 - Training & Qualification, Site Induction & Toolbox Talks | Site Supervision All Workers | 1 | 5 | M6 | Y | 0 | 1 | 0 | 0
Setting Up Equipment. | Back and shoulder injuries Cuts, abrasions and splinters Back strains when lifting material. | 3 | 4 | H7 | 1 - Set up equipment on level ground. Avoid rough & difficult terrain 2 - Use appropriate P.P.E equipment when required. 3 - Training in the setup of associated equipment. 4 - Use correct lifting technique - Refer SWMS Manual Handling | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Introduction to work site of EWP | Fall from Heights. Hit by moving plant and equipment. Pinch point injury | 3 | 4 | H7 | 1 - Ensure EWP has been introduced to site and stakeholders are aware. Only if required for project 2 - Ensure only trained employees use EWP. 3 - Ensure all servicing is current. 4 - Ensure correct procedure and use is adhered to. 5 - Ensure EWP is on level and stable ground. 6 - If required, ensure correct fall protection is utilised. 7 - No Skylarking. 8 - Reference - SWMS Elevated Work Platform | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Isolate Electrical Services If Required | Electrical Shock Eye Injuries Hearing injuries Falls Injuries to people below from falling objects Burns Skin irritations Excessive noise | 4 | 4 | H8 | 1 - Ensure all service is disconnected from electrical mains. On site labour to treat all power circuits as live. 2 - Ensure other power source from outside the site is identified and disconnected. Ensure workers use Volt Sticks are used to check for live circuits. 3 - Ensure other power source from outside the site is identified and disconnected. Ensure Earth Leakage Switch is installed on mains supply or generator 4 - Ensure irregular (‘bodgie’) connections are identified and disconnected. Ensure temporary connections are identified, tagged and isolated 5 - Warm up briefly beforehand. Keep back straight, eyes fixed straight ahead; lift with legs & not the back. 6 - Get help if load is too heavy or awkward. Don’t twist. 7 - Wear safety boots and gloves if necessary 8 - Visually check before use to make sure all safety features and guards are in place & there is no damage. Don’t operate in wet conditions 9 - Ensure earth leakage protections is in place and is at the supply end of the extension lead 10 - If device trips, don’t reset and start again until cause is found 11 - Switch tool off if any faults or abnormal actions become apparent 12 - Ensure tool action is stopped before setting down 13 - Wear appropriate PPE – safety glasses, ear protection Secure any loose hair and clothing 14 - Inspect ladder prior to use – make sure is in sound condition, clean and undamaged 15 - Use two person to carry if required 16 - Secure ladder to structure before climbing onto steps 17 - Have another person near the ladder supervising the area to support the ladder 18 - Wear appropriate footwear when climbing ladders 19 - Have three limbs on the ladder at all times 20 - Wear a tool pouch to carry tools 21 - Watch what is being done. Don’t be distracted by others and activities within the work areaIf device trips, don’t reset and start again until cause is found. | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Isolate Electrical Services If Required | Electrical Shock Eye Injuries Hearing injuries Falls Injuries to people below from falling objects Burns Skin irritations Excessive noise | 4 | 4 | H8 | 1 - Wear appropriate PPE – eye protection if sawing and sanding; steel capped boots 2 - Circuit dead locked off tagged and tested and proved dead, this work to be done by sire electrician. 3 - Drill 50mm holes in top of switch board and bush holes with cable bushing. 4 - Bring cable into switchboard. 5 - Terminate cables as per clients drawings 6 - Check cables for damage and conduct circuit testing with a meter 7 - Wear ful llength clothing, glasses and hearing protectionWhen working at heights above 2 metres, ensure appropriate fall protection is in place Carry out risk assessment prior to starting work: Locate power lines & stay at least 2 metres clean, Identify any other obstructions, Ensure ladders are placed on a level surface Barricade area to remove any dangers to other people in the area – this will isolate hazards and control the risks Inform client and site electrician. Barricade immediate area with warning signs. Have electrical rescue kit with a trained person on standby in electrical rescue and CPR | Site Supervision All Workers | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
Errecting Scaffold If Required | Scaffold Collapse Fall from heights Falling objects Overloading | 4 | 5 | E9 | 1 - Scaffold to be loaded as per scaffold duty classification 2 - Bricks & materials to be stacked over scaffold transoms to allow a minimum of 450mm passage way along working platform 3 - Do not stack bricks higher than platform handrail. 4 - Do not alter scaffold. 5 - Remove waste regularly 6 - Check scaff-tag & working platforms before use. Do not use if unsafe. 7 - Ensure all fall hazards are protected by handrail and brick guards. 8 - References - Approved SWMS Scaffolding, COP Managing the Risks of Falls, AS1576.1:2010 | Site Supervision All Workers | 1 | 5 | M6 |  | 0 | 1 | 0 | 0
Isolate Plumbing Services If Required | Manual handling/body stressing Slips/trips Back strain Muscle strain Impact injuries | 3 | 3 | M6 | 1 - Ensure hydraulic services are isolated at main source. 2 - Test various output prior to demolishing. | Site Supervision All Workers | 1 | 3 | L4 |  | 1 | 0 | 0 | 0
Hazardous Substances | Injury from exposure to hazardous substances such as concrete, concrete additives, sealing compounds. Injury due from contact with Flux Welding rods, Oxy acetylene, glues, adhesives | 3 | 5 | H8 | 1 - Manage chemicals/sunstances in accordance with Chemicals Management Program - Refer Hazardous Chemicals 2 - PPE in accordance with SDS 3 - Reference COP Managing the Risks of Hazardous Chemicals in the Workplace. | Site Supervision All Workers | 1 | 5 | M6 |  | 0 | 1 | 0 | 0
Working at Heights | Slips, trips and falls, cuts and abrasions, sprains and back injuries, impact injuries | 4 | 4 | H8 | 1 - Height Work must be in accordance with Safe Work requirements. Specific requirements include: 2 - Fall prevention in accordance with the SafeWork NSW Code of Practice - Managing the Risk of Falls at Workplaces 3 - Fall protection systems in accordance with AS1891:2007 4 - Isolate work areas below 5 - Mandatory Safety Helmets 6 - Refer Ladders uo to 2M | Site Supervision All Workers | 2 | 4 | M6 |  | 0 | 1 | 0 | 0
Site Safety; Securing redundant area. Barricades/ fencing and/or signage | Slips, trips and falls, cuts and abrasions, sprains and back injuries, impact injuries | 3 | 3 | M6 | 1 - Ensure Work areas are covered securely at the completion of works each day; 2 - Ensure adequate signage is securely installed at multiple points at the completion of works each day; 3 - Ensure that all barricades and fencing around the work site are well established and secure at the completion of works each day; 4 - Ensure all duty of care has been taken to establish a safe environment around the secured work area. 5 - Reference AS4687:2007 Temporary Fencing | Site Supervision | 1 | 3 | L4 |  | 1 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## General Works
General Works
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Preparatory Activities e.g. Undertake Measurements etc. | Slips, Trips & Falls Noise | 4 | 3 | H7 | 1 - Inspect work area prior to undertaking activities. Remove all obstacles. 2 - Wear hearing protection in designated areas or noisy environmentss | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Working at Heights - Scaffolding | Falls, Damage to persons, equipment and property | 4 | 5 | E9 | 1 - Ensure scaffolding is erected by ticketed personnel 2 - Ensure harness’s are worn and that all harness and ropes and fixing points are inspected prior to working on roof 3 - No one is to walk under any works carried out at heights | Site Supervision All Workers | 1 | 5 | M6 | 0 | 1 | 0 | 0
Remove Existing Materials | Dust, Cuts, Abrasions, Electrocution, Heavy Lifting | 4 | 3 | H7 | 1 - Wear correct PPE 2 - All leads are tagged 3 - Safe manual handling practices | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Remove Existing Materials | Falls - Work that is carried out near a trench or penetration with an excavated depth greater than 1.5 metres. | 4 | 4 | H8 | All open penetrations must be fenced or securely covered in accordance with the SafeWork NSW Code of Practice for Excavation Work – January 2020 | Site Supervision All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Remove Existing Materials | Exposure to Essential Services - work carried out on or near: • pressurised gas distribution mains or piping • chemical, fuel or refrigerant lines • energised electrical installations or services. | 4 | 4 | H8 | 1.All electric, gas, water, sewer, steam and other service lines not required during the works should be shut off, capped or otherwise controlled at, or outside, the building line before demolition work is started. 2.Notify utility agency in advance and obtain approval to shut down. Any service retained for the works should be adequately protected as required by the relevant authority – eg the protection of overhead electric lines. 3.Obtain current information on the services prior to commencing work and: i.have regard for the information ii.keep the information readily available for inspection 4.Under the WHS Act make the information available to any principal contractor and subcontractors 5.retain the information until the excavation is completed or, if there is a notifiable incident relating to the works, two years after the incident occurs. 6.The available information about existing underground essential services may not be accurate. Therefore, it is important that work methods include an initial examination of the area. | Site Supervision All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Install New Materials | Dust, Cuts, Abrasions, Electrocution, Heavy Lifting | 4 | 3 | H7 | 1 - Wear correct PPE 2 - All leads are tagged 3 - Safe manual handling practices | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Finish and Gap all Materials | Dust, Cuts, Abrasions, Electrocution, Heavy Lifting | 4 | 3 | H7 | 1 - Wear correct PPE 2 - All leads are tagged 3 - Safe manual handling practices | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Remove and Load Waste | Dust, Cuts, Abrasions, Electrocution, Heavy Lifting | 4 | 3 | H7 | 1 - Wear correct PPE 2 - All leads are tagged 3 - Safe manual handling practices | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Work Place Aggression | Physical injury, Damage to Persons, Equipment and Property | 3 | 3 | M6 | 1 - Ensure all disagreements and disputes are forwarded to the site supervisor and or project manager for clarification. | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Pedestrians and Traffic | Physical injury, Damage to Persons, Equipment and Property | 4 | 3 | H7 | 1 - Ensure site security fencing is securely in place. 2 - Ensure appropriate traffic measures are implemented if required to notify pedestrians and drivers of potential hazard. 3 – Traffic Management Plans (TMP) developed and implemented by qualified providers. | Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## General Demolition
General Demolition
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Site Environment | All workers unaware of site issues. Slips trips and falls Manual Handling Noise Fatigue | 3 | 4 | H7 | 1 - Site office or muster point to be established with all required information including induction and sign in to be available to all staff attending site. 2 - Toolbox Talks 3 - Ensure site rules are adhered to at all times. 4 - Ensure site traffic management plan is adhered to. 5 - Correct PPE to be worn - Site Safety Rules 6 - Site Working Hours. | All Workers Site Supervision | 1 | 4 | M5 | 0 | 1 | 0 | 0
Access & Egress - Traffic Management | Injury due to Vehicle Collision - Collision with pedestrians and site vehicles | 3 | 4 | H7 | 1 - Traffic Management Plan 2 - Area to be barricaded/fenced from unauthorised access. 3 - Establish protection of tree protection environmental management as per scope of works this will include isolating area to protect it from the intended works. | Project Management | 1 | 4 | M5 | 0 | 1 | 0 | 0
Demolition | General Activities | 4 | 3 | H7 | 1 - Subcontractor to Implement controls as per approved SWMS. 2 - Demolition in accordance with the requirements of relevant legislation, COP – Demolition Work, COP – Managing Risks of Plant in the Workplace, Standards (AS 2601) 3 - Effective Training & Qualification Management 4 - Site Induction & Toolbox Talks. | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Overhead Wires | Electrocution | 3 | 5 | H8 | 1 - Overhead Wires Identified Using "Tiger Tails" 2 - Safe Distance Assessment - Mandatory Minimum Approach Distances As Per SafeWork NSW COP Working Near Overhead Power Lines 3 - Use of Spotter 4 - Safe Effective Hazardous Working at Heights Procedures 5 - Training & Qualification, Site Induction & Toolbox Talks. | Operator Site Supervision | 1 | 5 | M6 | 0 | 1 | 0 | 0
Heritage | Damage to Heritage Structures | 3 | 4 | H7 | 1 - Assessment of Structural Integrity of Building 2 - Exclusion Zones & Barricading 3 - Approved Sub-Contractor SWMS Demolition & Temporary Support of Load Bearing Structures | Project Management | 1 | 4 | M5 | 0 | 1 | 0 | 0
Working at Heights | Slips, trips and falls, cuts and abrasions, sprains and back injuries, impact injuries | 4 | 4 | H8 | 1 - Height Work must be in accordance with Safe Work requirements. Specific requirements include: a) Fall prevention in accordance with the SafeWork NSW Code of Practice - Managing the Risk of Falls at Workplaces b) Fall protection systems in accordance with AS1891:2007 2 - Isolate work areas below 3 - Mandatory Safety Helmets. | Project Management | 2 | 4 | M6 | 0 | 1 | 0 | 0
Demolition | Manual Handling | 4 | 3 | H7 | 1 - Warm up briefly beforehand 2 - Keep back straight, eyes fixed straight ahead; lift with legs & not the back 3 - Get help if load is too heavy or awkward. 4 - Don’t twist 5 - Reference - COP Hazardoous Manual Tasks | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Hot Work - Fire, Explosion | 3 | 5 | H8 | 1 - Hot work permit system including observer | All Workers Site Supervision | 1 | 5 | M6 | 0 | 1 | 0 | 0
Demolition | Impact injuries Debris and tools materials | 4 | 4 | H8 | 1 - Supervision only if structurally not stable. 2 - Use the correct tool for the task and train workers. 3 - Correct use of PPE. 4 - Only competent operators to use machinery. 5 - Isolation zone to be set up. 6 - Visually check before use to make sure all safety features and guards are in place & there is no damage. | All Workers Site Supervision | 1 | 4 | M5 | 0 | 1 | 0 | 0
Demolition | Risk to persons not involved with the project i.e. public | 4 | 3 | H7 | 1 - Ensure site is isolated and only authorised personal to gain entry. 2 - All visitors to be escorted. | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Minor injury from hand tools | 3 | 3 | M6 | 1 - Ensure correct use of tools to be adhered to as per training. 2 - Wear appropriate PPE. | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Eye injury | 3 | 3 | M6 | 1 - PPE Eye protection | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Injury to Staff from debris | 3 | 3 | M6 | 1 - Appropriate PPE to the conditions. 2 - Safety Helmets Mandatory | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Slips trips and falls | 3 | 3 | M6 | 1 - General site knowledge and housekeeping. 2 - Toolbox Talks | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | Irritation of skin, lungs, breathing | 4 | 3 | H7 | 1 - PPE and ensure no carciogenic materials are being disturbed, review HAZMAT register. | All Workers Site Supervision | 1 | 3 | L4 | 1 | 0 | 0 | 0
Demolition | HAZARDOUS materials including ACM, Lead. | 3 | 5 | H8 | 1 - Ensure HAZMAT REPORT has been reviewed test any suspicious martial before commencement of work. 2 - Lead dust over 1% concentration requires a lead work permit. | Management | 1 | 5 | M6 | 0 | 1 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Removal of ACM
Removal of ACM
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Site Preparation | Inadequate Assessment of the Risks Associated with the Specific Asbestos Removal | 4 | 4 | H8 | 1 - Conduct a thorough risk assessment before starting any asbestos removal project. 2 - Identify potential hazards, assess the level of risk, and develop a comprehensive plan to mitigate those risks. | Site Supervision | 1 | 4 | M5 | 0 | 1 | 0 | 0
Site Preparation | Unauthorised Personnel Approaching the Site | 3 | 3 | M6 | 1 - Establish a containment area around the work site using barriers and negative pressure enclosures to prevent the spread of asbestos fibers. 2 - Clearly mark the work area, and restrict access to unauthorised personnel. 3 - Ensure prestart meeting takes place and all staff and subcontractors aware of their roles responsibilities. 4 - Ensure correct asbestos signage in place. 5 - Nominated person to ensure that unauthorised personnel do not enter work area. | Site Supervision | 2 | 2 | L4 | 1 | 0 | 0 | 0
Assess Condition of ACM to Ensure it is not Friable. | Unauthorised Personnel Approaching the Site | 4 | 5 | E9 | 1 - Perform visual inspection of ACM if it appears to be in a dry, powder form then it is to be deemed friable. 2 - If ACM is friable discontinue recovery work. 3 - Wet down ACM with water spray Wipe down any contaminated PPE, tools. 4 - Rags and Disposable PPE to be placed into bag. Ensure personal and work area decontamination. 5 - Clearance required before public access by a Licenced Asbestos Assessor. 6 - Place bag into 2nd labelled asbestos bag. Tie off bag and prepare for transport to asbestos waste bin. Seal to be goose necked. 7 - Inform supervisor/manager of friable ACM requiring a licenced “A” removalist is to be arranged. | Site Supervision | 1 | 5 | M6 | 0 | 1 | 0 | 0
Prepare Water Spray System | ACM-Airborne Fibre Release | 4 | 4 | H8 | 1 - Continuous water spray system is preferred, however, if unavailable small manual pressurised system is appropriate. E.g. garden sprayer. 2 - Alternative- spray ACM with PVA solution. | Site Supervision / All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Removal of Existing ACM | ACM-Airborne Fibre Release | 3 | 4 | H7 | 1 - Use appropriate personal protective equipment, including: a) Respiratory protection (such as respirators with high-efficiency particulate air filters) b) Coveralls c) Gloves d) Eye protection. 2 - Regularly check and maintain the PPE to ensure its effectiveness. 3 - Use wet methods to suppress the generation of airborne asbestos fibers. 4 - Keep materials containing asbestos damp during removal to minimize fiber release. 5 - Employ techniques that minimise the disturbance of asbestos-containing materials. 6 - Implement effective ventilation systems to control the concentration of airborne asbestos fibers. Conduct air monitoring before, during, and after removal to ensure that asbestos levels are within acceptable limits. | Site Supervision / All Workers | 2 | 2 | L4 | 1 | 0 | 0 | 0
Site Clean Up | ACM-Airborne Fibre Release | 3 | 4 | H7 | 1 - Carefully fold poly sheeting, capturing any ACM debris. 2 - Place the sheeting into asbestos disposal bag. 3 - Ensure correct documentation completed to track ACM disposal. | Site Supervision / All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Decontamination | General Contamination by ACM | 3 | 3 | M6 | 1 - A separate decontamination area shall be established by using (where practicable) a second sheet of plastic for decontamination activities. 2 - Where this is not possible due to wind or restricted access then a larger sheet of plastic may be used, it shall we weighted down and two separate areas identified by a marked line or similar. One area shall be used for work and the second area for decontaminated items. 3 - The decontamination area shall be as close as possible to the work area. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Decontamination - Hand Tools | General Contamination by ACM | 3 | 3 | M6 | 1 - All hand tools used during the removal of ACM, must be decontaminated. 2 - Take required hand tools to the decontamination zone. 3 - Only Workers who were involved in the ACM removal work and are wearing the required PPE may participate in decontamination. 4 - Whilst standing on the poly sheeting, ensure hand tools are wiped down using damp cloths (unless tool is being disposed). 5 - The hand tools should be placed in the dedicated sealable container or in an asbestos disposal bag. 6 - Cloths used for decontamination are to be disposed of in an asbestos disposal bag. Tools to be placed on plastic sheeting to prevent contamination. 7 - Place contaminated rag in plastic asbestos waste bag. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Decontamination - Personnel | General Contamination by ACM | 3 | 3 | M6 | 1 - Once decontamination of hand tools is complete, personal decontamination of Workers is to occur. 2 - Dispose of cloths in an asbestos disposal bag. 3 - Remove tape from cuffs (ankles and wrists). 4 - Remove gumboots and glasses and wipe down with damp cloths. Dispose of cloths in an asbestos disposal bag. 5 - Gumboots and glasses must be placed in a dedicated sealable container marked with the following wording; ‘Asbestos Dedicated Protective Equipment - Not to be used on Non Asbestos Work’. 6 - Carefully fold the poly sheeting on the ground in the decontamination area and dispose of sheeting in an asbestos disposal bag. 7 - Carefully remove coveralls turning them inside out to trap any remaining dust or debris. Take off disposable gloves place in the inner bag and seal the inner bag by picking it up and twisting the inner bag. Folding it over to form a ‘goose neck’. Wrap the ‘goose neck’ in duct tape 8 - Wash hands thoroughly. Ensure that the P2 disposable mask is the last item of PPE removed. Now place the mask into the outer bag and seal by picking it up and twisting the outer bag. Folding it over to form a ‘goose neck’. Wrap the ‘goose neck’ in duct tape. Wash hands thoroughly. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Waste Disposal | General Contamination by ACM | 3 | 4 | H7 | 1 - Place poly sheeting in the work area to capture any loose pieces. 2 - Keep pieces as large as possible and place into double bagged asbestos disposal bags. If pieces will not fit into the asbestos disposal bags DO NOT BREAK UP FURTHER, double wrap them in 200 micron poly sheeting. 3 - Wrap piece of ACM in poly sheeting like a present and tape up. 4 - Use asbestos warning tape or other appropriate asbestos identifier to label the outer layer of poly sheeting. 5 - Place the sheeting into either the wrapped and sealed poly sheeting or asbestos disposal bag. 6 - Dispose of all contaminated clothing as asbestos waste. 7 - Procedure for packing ACM: a) Seal the inner bag by picking it up and twisting the inner bag, folding it over to form a ‘goose neck’. b) Wrap the ‘goose neck’ in duct tape. c) Seal by picking it up and twisting the inner bag. Folding it over to form a ‘goose neck’. Wrap the ‘goose neck’ in duct tape 8 - Do not overfill bags beyond half full. Make sure bags are 20-25kg in weight. When lifting poly sheeting or asbestos disposal bags that are heavy, ensure manual handling techniques are followed. | Site Supervision / All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Transport of ACM | General Contamination by ACM | 3 | 4 | H7 | 1 - Asbestos waste bags shall be protected during transport. 2 - The load should not be carried inside the passenger compartment of a vehicle. 3 - ACM bags shall be covered with shade cloth and all materials in a trailer and ute shall be covered by a mesh restraint (50 x 50mm hole size). 4 - Loads up to 250 kg may be carried in unlicensed vehicles under the current EPA exemption. 5 - ACM material is to be transported off site as soon as reasonably practicable. At the end of each day if the asbestos waste cannot be secured at the removal site it shall be returned to base. 6 - Attach location tag and complete Asbestos material certificate form. | Site Supervision / All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Miscellanous Tasks | Slips, Trips, Falls | 3 | 3 | M6 | 1 - Ensure that the work area is kept clean and clear of debris at all times. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Miscellanous Tasks | Manual Handling | 3 | 3 | M6 | 1 - Follow manual handling procedures. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Miscellanous Tasks | Noise | 3 | 3 | M6 | 1 - Hearing protection as required. | Site Supervision / All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Working at Heights
Working at Heights - Ladders Up to 2M
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Preparation for Use | Injury from incorrect or faulty ladder Manual Handling Slips and Falls | 3 | 3 | M6 | 1 - Use correct ladder for the job 2 - Only use an industrial ladder 120kgs and fitted with rubber or similar non slip material feet. 3 - Metal ladders or wire reinforced ladders not to used where electrical hazards exist 4 - Examine ladder for any defects or damage before use 5 - Long and heavy ladders (greater than 20kgs) should be handled by at least two people 6 - Wear slip resistant footwear when using ladders | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Set Up Ladder | Ladder slipping, falling or collapsing causing personal injury or damage to property | 3 | 3 | M6 | 1 - Do not place ladders in vehicle or pedestrian thoroughfare 2 - Use a second person or physical barrier to ensure the ladder is not knocked by passing traffic or pedestrians 3 - Ladder to be adequately supported at the base to ensure it is level and won’t sink into or slide on surface 4 - Set ladder at a slope of 4 in 1 – angled one out and four up 5 - Ladder should extend one metre above access level 6 - Ladder to be firmly secured or tied off or held firmly by another person 7 - The ties should be attached to the stiles of the ladder and not the rungs 8 - Step ladders should only be used in the fully open position | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Ascending & Descending Ladder | Fall from Heights | 3 | 4 | H7 | 1 - Climb and descend facing the ladder maintaining three points of contact with the hands gripping the stiles or each rung 2 - Do not carry anything in your hands while climbing or descending 3 - Do not climb higher than the third rung from the top of the ladder 4 - Face the ladder when working from it 5 - Clean off footwear and ladder rungs before using the ladder each time 6 - Three body limbs on the ladder at all times three points of attachment | All Workers | 2 | 4 | M6 | 0 | 1 | 0 | 0
Working from Ladders | Ladder falling or collapsing Slips and falls causing personal injury Falling from heights | 3 | 4 | H7 | 1 - One person at a time on the ladder 2 - Three body limbs on the ladder at all times three points of attachment 3 - Only work on a job within easy arm’s reach 4 - Do not over reach. 5 - Do not straddle the ladder 6 - Do not use equipment or tools that are primarily designed to be used with 2 hands. 7 - Make sure that no one works under the ladder 8 - Ladder is not to be walked by the person standing on the ladder | All Workers | 2 | 4 | M6 | 0 | 1 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Power Tools
Portable Electrical Tools
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Inspect Tools & Work Area | Electric shock to operator. Operator may receive electric shock. Eye and hearing damage can result from flying debris. Exposure to live power through electrical leads with no earth leakage protection. Exposure to live power through electrical leads on ground. Exposure to live power form sub-panel. | 4 | 4 | H8 | 1 - Then tool must not be used in wet conditions. All leads must be positioned off the ground and have current inspection tag. 2 -Tool must be fitted with a protective residual current device which must be in operational condition. 3 - Eye protection i.e. Safety glasses, goggles must be worn. Hearing protection i.e. ear muffs, ear plugs must be worn. 4 - Earth leakage protection on all temporary power boards must be provided. 5 - Portable earth leakage units to be used in all other cases. 6 - Keep all electrical leads elevated and clear of work areas. 7 - Lockout and tag sub panel during electrical work. | Supervisor / Operator | 1 | 4 | M5 | 0 | 1 | 0 | 0
Inspect Leads | Leads may be damaged or not have current tag. Electric shock to operator. | 4 | 4 | H8 | 1 - Inspect leads for damage and current inspection tag. If defect found, tag tool out. 2 - Test & Tag in accordance with the requirements of AS3760:2010 | Supervisor / Operator | 1 | 4 | M5 | 0 | 1 | 0 | 0
Check for Services - Gas, power, etc | Hidden services may come in contact with tool causing injury | 3 | 4 | H7 | 1 - Ensure that positions of all services are known and marked. 2 - Tool must not be allowed to come into contact with services. | Supervisor / Operator | 1 | 4 | M5 | 0 | 1 | 0 | 0
Fitting the Accessory to the Tool | Accessory may dislodge and injure operator | 3 | 2 | M5 | 1 - Ensure that retainer latch on stirrup is in closed position and that recess in the accessory faces the latch pins. | Supervisor / Operator | 2 | 2 | L4 | 1 | 0 | 0 | 0
Test the Tool and Begin Work | Stop Control May Not Operate | 3 | 4 | H7 | 1 - Check operation of stop switch. If defective tag machine out. Work tool to open end of work to avoid jamming | Supervisor / Operator | 1 | 4 | M5 | 0 | 1 | 0 | 0
Operating the Tool Accessories | Tool may jam and injure operator | 3 | 3 | M6 | 1 - Operate tool to open edge of work. Clear hole periodically to avoid jamming. | Supervisor / Operator | 1 | 3 | L4 | 1 | 0 | 0 | 0
Release the Trigger, Isolate the Tool and Remove Accessory | Accidental start up may injure hands and fingers | 3 | 3 | M6 | 1 - Stop the tool at trigger. Isolate the power at source before removing the accessory. | Supervisor / Operator | 1 | 3 | L4 | 1 | 0 | 0 | 0
Clean Drills and Store in Container | Clean tool may allow operator to see defect. | 3 | 3 | M6 | 1 - Examine drills for defects, tag tool out if any found. Store in secure place. | Supervisor / Operator | 1 | 3 | L4 | 1 | 0 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Hazardous Chemicals
Hazardous Chemicals
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  | Reference the SDS Folder on site before proceeding with handling any chemical found or used. Use the QR Code provided in the site documents to access the online SDS Library. |  | Residual Risk
Elimination | Eliminate the use of the substances. | 4 | 3 | H7 | Using a physical process instead of a chemical process e.g. using an ultrasound to clean equipment instead of a process involving chemicals; using clips/bolts or nails instead of adhesive. | Management | 1 | 3 | L4 | 1 | 0 | 0 | 0
Identification | Incorrect use or handling | 3 | 3 | M6 | Reference the SDS Folder in on site before proceeding with handling any chemical found or used | All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Substitution | Use a safer substance or a safer form of the substance. | 4 | 4 | H8 | Safe Substance 1 - Use detergent instead of chlorinated solvent for cleaning. 2 - Use water-based chemicals instead of solvent – based. 3 - Chemicals where compatible. Safer Form or Process 1 - Paint with a brush instead of spraying. 2 - Purchase a substance in a safer form. | Management Supervision All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Isolation | Separate people or property from the substance by distance or barriers | 3 | 3 | M6 | 1 - Used closed systems. 2 - Isolate the process in a room with restricted access use appropriate barriers to separate substances. 3 - Distance workers from substances/processes through the use of remote controls. 4 - Distance property, incompatible chemicals and ignition sources from goods. | Management Supervision All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Engineering | Use physical controls (such as plant/equipment) that eliminate or reduce the generation of substances; suppress or contain substances; or limit the area of contamination in the event of spills and leaks. | 3 | 3 | M6 | 1 - Use fully or partially enclosed ventilation booths. 2 - Fully or partially enclose the process with exhaust extraction. 3 - Use local exhaust or natural ventilation systems 4 - Design buildings that are: compatible with the intended goods; made of non-combustible construction as far as is practicable; designed to reduce contamination. 5 - Use Bunding to contain spillage. 6 - Install drains, tanks or sumps to cope with spilled material. 7 - Install automatic fire protection and chemical suppression systems | Management Supervision All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Administration | Use safe work practices including good housekeeping. | 4 | 3 | H7 | 1 - Reduce the amount of property or the number of employees exposed. 2 - Reduce the duration and/or frequency of exposure e.g. through job rotation. 3 - Reduce the amount of goods/products stored and used. 4 - Ensure safe interim storage of wastes/products (e.g. labelled properly in suitable containers stored away from people, the environment, incompatible chemicals, 5 - Vacuum or wet sweep to suppress dust being generated. 6 - Cover containers and make sure lids are attached. 7 - Clean up spills immediately (includes provision of suitable aids and equipment). 8 - Ensure there is no eating, drinking or smoking in areas where substances are used. 9 - Provide suitable washing facilities. 10 - Instruct employees on how to use substances/equipment safety. | Management Supervision All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Personal Protective Equipment (PPE) | Provide protective clothing and equipment for employees, supervisors and visitors. NB: Items must be compatible with chemical(s) being used/stored. | 4 | 3 | H7 | 1 - Overalls, aprons, gowns, chemical resistant suits. 2 - Footwear (enclosed shoes, safety boots). 3 - Gloves. 4 - Chemical resistance glasses (safety glasses). 5 - Face shield/masks, respirators (full or partial). 6 - Head protection | Management Supervision All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Synthetic Mineral Fibres | 1 - Irritation of the Respiratory Tract. 2 - Skin and Eye Irritation 3 - Environmental Concerns | 4 | 3 | H7 | 1 - Engineering Controls a) Ventilation b)Dust Suppression c) Isolation d) Automated Handling 2 - Administrative Controls a) Work Procedures and Training b) Regular Cleaning c) Restricted Access 3 - PPE a) Respiratory Protection b) Protective Clothing c) Eye Protection d) Hygiene Facilities 4 - Safe Disposal and Environmental Controls a) Waste Management b) Environmental Monitoring c) Transport Precautions | Management Supervision All Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
[10 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Hot Works
Hot Works
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Hot Work | Fire Burns Explosions | 4 | 5 | E9 | 1 - Hot Work Permit approved prior to commencement of work. 2 - Operator is qualified and competent to perform this task. 3 - Have a fire extinguisher readily available for all hot work. 4 - Use fire resistant blanket when cutting or welding near combustible materials.6 - Use Fire Watch as required by assessed risks. | Supervision All Workers | 1 | 5 | M6 | 0 | 1 | 0 | 0
Hot Work | Asphyxiation | 4 | 5 | E9 | 1 - Flash back arrestors fitted to both handpiece and bottles of oxy/acetylene/LPG equipment. Ensure gas supply is turned off & hoses disconnected if the equipment is left unattended and when a Confined Space is vacated. 2 - Removal of hand piece when not in Confined Space. 3 - Natural ventilation or mechanical ventilation using fans. 4 - No ignition source is introduced into a confined space if the risk of fire or explosion is present (such as requiring the use of intrinsically safe equipment, etc.). 6 - Use Fire Watch as required by assessed risks. | Supervision All Workers | 1 | 5 | M6 | 0 | 1 | 0 | 0
Hot Work | Foreign Bodies in Eye | 3 | 4 | H7 | 1 - Double Eye protection to be worn for all grinding activities – clear safety foam back safety glasses under a face shield is the minimum standard due to the confined nature of the work. 2 - Upgrade safety glasses to mono goggles in dusty conditions. 3 - Alternately an ad flow helmet can be worn | Supervision All Workers | 1 | 4 | M5 | 0 | 1 | 0 | 0
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Manual Handling
Manual Handling
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Site Environment | All workers unaware of site issues. Slips trips and falls Manual Handling Noise Fatigue | 3 | 4 | H7 | 1 - Site office or muster point to be established with all required information including induction and sign in to be available to all staff attending site. 2 - Toolbox talks 3 - Ensure site rules are adhered to at all times. 4 - Ensure site traffic management is adhered to 5 - Correct PPE to be worn - Site Safety Rules 6 - Site Working Hours | All Workers Site Supervision | 1 | 4 | M5 |  | 0 | 1 | 0 | 0
General Manual Handling | Impact Injuries, Sprains & Strains | 4 | 3 | H7 | 1 - All manual handling activities in accordance with the NSW COP - Hazardous Manual Tasks August 2019 | All Workers | 2 | 3 | L4 |  | 1 | 0 | 0 | 0
General Manual Handling | Impact Injuries, Sprains & Strains | 4 | 3 | H7 | 1 - Warm up briefly beforehand. 2 - Keep back straight, eyes fixed straight ahead; lift with legs & not the back. 3 - Get help if load is too heavy or awkward. 4 - Don’t twist. | All Workers | 2 | 3 | L4 |  | 1 | 0 | 0 | 0
General Manual Handling | Slips, Trips & Falls | 4 | 4 | H8 | 1 - House keeping 2 - Site induction 3 - Toolbox talks 4 - Ensure site rules are adhered to at all times. 5 - Site Inspections 6 - Reference - NSW COP Managing the Workplace and Facilities August 2019 | All Workers | 2 | 4 | L4 |  | 1 | 0 | 0 | 0
Working at Heights | Slips, trips and falls, cuts and abrasions, sprains and back injuries, impact injuries | 4 | 4 | H8 | 1 - Height Work must be in accordance with requirements. 2 - Specific requirements include: 3 - Fall prevention in accordance with the NSW Code of Practice - Managing the Risk of Falls at Workplaces August 2019 4 - Fall protection systems in accordance with AS1891:2007 5 - Isolate work areas below 6 - Mandatory Safety Helmets | Project Management | 3 | 4 | M5 |  | 0 | 1 | 0 | 0
Movement of Materials | Back strain Muscle Strain Impact Injuries | 4 | 3 | H7 | 1 - Warm up briefly beforehand 2 - Keep back straight, eyes fixed straight ahead; lift with legs & not the back 3 - Get help if load is too heavy or awkward 4 - Don’t twist 5 - Use correct manual handling technique | All Workers | 3 | 3 | M5 | Y | 0 | 1 | 0 | 0
Unloading Equipment | Fall from vehicle Manual Handling injury Sprains Strains and Falls | 3 | 3 | M6 | 1 - Manual handling The use of PPE equipment such as gloves are needed. 2 - Team lifting where required and manual handling aids when possible. 3 - Use of correct lifting technique when carrying out work. 4 - Ensure stretching and warm up prior to work being carried out. | All Workers | 2 | 3 | L4 | Y | 1 | 0 | 0 | 0
[11 empty] | #REF! | #REF! | #REF! | #REF!
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Traffic Control
Traffic Control
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Preparation | Inadequate Planning. | 4 | 3 | H7 | 1 - Identify people, equipment, PPE, potential hazards and safety controls prior to commencement of works. 2 - Site induction for all employees’ to know role for each job. 3 - Conduct induction/toolbox meetings to explain contents of the safe work method statement. 4 - Discuss all hazards and control measures related to the work to be carried out. 5 - Consult with employees and suppliers performing this work, and seek input in the final version prior to works begin. 6 - Team Leader to issue traffic management plan to work crew. 7 - All relevant signs to be placed on or around vehicles. 8 - Vehicles parked legally. 9 - All services to be located before commencement of works begin and marked on road way with depth. | Site Supervision / Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Traffic & Pedestrian Control Plan | Injuries / collisions to work personnel also damage to work plant / work equipment. Injuries / collisions to the general public also damage to public vehicles. | 3 | 4 | H7 | 1 - Note assessed risks and control measures on JSA form prior to commencing work activity or as required during the day. 2 - Work personnel not to engage in any work activity until the traffic / pedestrian control plan is in place. 3 - Obey all directions given by professional control personnel and traffic control / pedestrian control set ups (Start / completion timings etc) 4 - ROL and traffic / pedestrian control plan to be produced by customer and or PROCAB personnel by use of approved scenario cards. 5 - Water filled barricades to be placed between traffic and work site where possible. If no water filled barricades can be placed, lane closure will apply as per the ROL and TCP constrains | Site Supervision / Workers | 2 | 4 | M6 | 0 | 1 | 0 | 0
Placing Traffic Control Devices at Worksite | Poor drivers Inappropriately traffic control measures Flora & fauna Through local traffic Manual Handling injuries Overgrown vegetation Cluttered surface | 3 | 4 | H7 | 1 - Follow traffic management plan from team leader. 2 - Ensure the traffic control measures are appropriate for all weather conditions (especially the wind on the road). 3 - Stay alert for traffic on worksite. 4 - All vehicles will turn at intersection/gateways when placing devices out. 5 - High visibility clothing must be worn by all employees plus all sub-Contractors who are worn on site. 6 - Safety boots to be worn. 7 - Spotters to be used. 8 - All rotary beacons must be turned on in work vehicles. 9 - Yellow card training required by all staff. 10 - Use extra people to make the job safer and lighten the load. 11 - Lift within your capacity. 12 - Worksite to be assessed prior to commencement of works and any hazards roadside vegetation to be slashed or removed. 13 - Worksite to be assessed daily to assess the traffic management plan. | Site Supervision / Workers | 2 | 4 | M6 | 0 | 1 | 0 | 0
Construction Work on Footpath | Through local traffic & pedestrians Plant / machinery Crushing | 3 | 3 | M6 | 1 - Traffic controlled as per Traffic scenario Cards. 2 - Vehicles Parked Legally with Signage and Cones. 3 - Staff to be aware of their surroundings and machinery in operations. 4 - Yellow card training required for all staff. | Site Supervision / Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Adding Material to Site | Tipping Loads Plant/machinery Overhead services Through local traffic | 3 | 3 | M6 | 1 - All employees have and sub-contractors to be well clear of trucks when tipping loads of materials. 2 - Staff to be aware of their surroundings and machinery in operations. 3 - A spotter may be required when tipping loads if trucks are near overhead services. 4 - Traffic controlled as per traffic management plan. | Site Supervision / Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Reinstatement | Tipping Loads Plant / machinery Through local traffic | 3 | 3 | M6 | 1 - All employees have and sub-contractors to be well clear of trucks when tipping loads of materials. 2 - Staff to be aware of their surroundings and machinery in operations. 3 - Traffic controlled as per traffic management plan. | Site Supervision / Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Clean up Worksite | Manual Handling | 3 | 3 | M6 | 1 - Use extra people to make the job safer and lighten the load. 2 - Lift within your capacity. | Site Supervision / Workers | 1 | 3 | L4 | 1 | 0 | 0 | 0
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Monitor & Review
Monitor & Review
Task | Hazard | Probability | Consequence | Ranking | Control | Person Responsible | Probability | Consequence | Ranking
|  | Inherent Risk |  |  |  |  | Residual Risk
Implementation |  | 4 | 4 | H8 | 1 - Company policies and procedures. 2 - Construction and Rail Industry Inductions. 3 - SWMS Briefings and Sign Off by Operators. Any changes during colsultation are incorporated into the SWMS and Workers briefed on changes. 4 - All relevant permits and approvals obtained prior to commencement of work. | Management Supervision Work Team | 1 | 1 | L2 | 1 | 0 | 0 | 0
Monitor |  | 4 | 4 | H8 | 1 - SWMS to be reviewed by all staff through daily pre-start and weekly toolbox talks for effectiveness & application to site. 2 - Compliance to the SWMS is monitored using a system of routine or random workplace inspections. 3 - In the event that the work is not being carried out in accordance with the SWMS, all work will cease immediately. SWMS are reviewed to identify non-compliance and ensure the method in the SWMS is the most practical and safest way of doing the task. The SWMS is revised if another method is identified as being a safer option, before work resumes. 4 - Feedback to be given by all staff and improvements to be included in revision of SWMS. 5 - In the event of changes to SWMS, workers are briefed on changes and sign off on revised SWMS. | Management Supervision Work Team | 1 | 1 | L2 | 1 | 0 | 0 | 0
Review |  | 4 | 4 | H8 | SWMS are reviewed under the following circumstances: 1 - Following an incident. 2 - If the SWMS is deemed impractical through consultation with Workers. 3 - If new hazards have been identified. 4 - If the work method has changed including changes to the workplace, environment, a system of work, a process or a procedure. 5 - On restarting the activity after a significant break. 6 - At the request of a HSR. 7 - Annually if none of the above. | Management Supervision Work Team | 1 | 1 | L2 | 1 | 0 | 0 | 0
Note on D2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Low (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on E2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.
Note on I2: 5-Almost Certain-Can be expected to occur in most circumstances. 4-Likely- (Quite Probable) Could occur in most circumstances. 3-Possible (Unlikely but possible)-Could happen in unusual circumstances. 2-Unlikely (Remotely possible)-Would only occur where multiple system or control failures occurred. 1-Negligible (Conceivable but unlikely)-Little or no chance of occurrence would require a combination of unusual factors and system and behavioural failures.
Note on J2: 5 – Critical - Death, environmental impact on or off-site with irreparable effect, huge financial loss from damage or interruption to business. (H) Life-threatening or disabling disease. 4 – Major - Life-threatening incident resulting in extensive injuries or major health effects, on or off-site environmental impact with detrimental effects, major loss from damage or interruption to business. (H) Irreversible health effect of concern. 3 – Moderate - Injury requires medical treatment, environmental on-site or off-site release able to be contained and rehabilitated, and medium financial loss from damage or business interruption. (H) Severe, reversible health effects of concern. 2 – Minor - Minor first aid injury, minimum environmental impact and low financial loss from damage or business interruption. (H) Reversible health effects of concern. 1 – Insignificant - No injuries, negligible environmental impact or financial loss from damage or business interruption. (H) Reversible health effects of little concern, or no adverse health effects.

## Sign Off
Sign Off
The representatives of Ages Build listed below have been involved in the creation and implementation of this Safe Work Method Statement (SWMS) and will make sure all work is carried out in accordance with this document. All workers listed below have the appropriate licence/qualifications and/or experience required to perform each job task:
Workers Name | Role | Signature | Date

## Data (hidden)
| 1 | 2 | 3 | 4 | 5
1 | L2 | L3 | L4 | M5 | M6
2 | L3 | L4 | M5 | M6 | H7
3 | L4 | M5 | M6 | H7 | H8
4 | M5 | M6 | H7 | H8 | E9
5 | M6 | H7 | H8 | E9 | E10
[6 empty] | Probability | No Incident or Injury | Medical Treatment | Lost Time Injury | Serious Injury | Fatality
[6 empty] | Negligible | Low | Low | Low | Moderate | H15
[6 empty] | Unlikely | Low | Low | Moderate | Moderate | H10
[6 empty] | Possible | Low | Moderate | H13 | H9 | E6
[6 empty] | Likely | H16 | H12 | E8 | E5 | E3
[6 empty] | Almost Certain | H11 | E7 | E4 | E2 | E1